SOFTWARE QUALITY ASSURANCE (SQA)

PROCESS

Version 1.4

September 4, 1997

Software Engineering Process Office (SEPO), D13

Space and Naval Warfare Systems Center (SPAWARSYSCEN)

53560 Hull Street

San Diego, CA 92152-5001

SOFTWARE QUALITY ASSURANCE (SQA)

PROCESS

Version 1.4

September 4, 1997

_____________________________________

Developed by Ann Hess, Software Engineering Process Office, D13, SPAWARSYSCEN SAN DIEGO CA

_____________________________________

Approved by Elizabeth Gramoy, Director, Software Engineering Process Office, D13, SPAWARSYSCEN SAN DIEGO CA

Administrative Information

Software Engineering Process Office, D13

Space and Naval Warfare Systems Center (SPAWARSYSCEN)

53560 Hull Street

San Diego, CA 92152-5001

SOFTWARE QUALITY ASSURANCE (SQA) PROCESS

Version 1.4

This document supersedes version 1.3  as guidance on the Software Quality Assurance Process at Space and Naval Warfare Systems Center (SPAWARSYSCEN SAN DIEGO CA).  SEPO assumes responsibility for this document and updates it as required to meet the needs of users within SPAWARSYSCEN SAN DIEGO CA.  SEPO welcomes and solicits feedback from users of this document so that future revisions of this document will reflect improvements, based on organizational experience and lessons learned.

If you have any questions or comments regarding this document please feel free to communicate them via the Document Change Request (DCR) form located at the back of this document.

Approved for public release; distribution is unlimited.

Ann Hess, SEPO, SPAWARSYSCEN SAN DIEGO CA, D13

Voice:  (619)553-3351,  Fax:  (619)553-6249, Internet:  hess@spawar.navy.mil

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D - DELETED

| CHANGE NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |
| 1 | 8/19/ 1997 | Complete document | M | (1) Correct discrepancies. | 1 |
|  |  |  | M | (2) Move “Establish SQA Organization” before “Identify/Select SQA Tasks”. |  |
|  |  |  | M | (3) Moved terms and definition to Section 10 and include list of acronyms. |  |
| 2 | 9/4/97 | Complete document | M | (1) Change references from NRaD to SPAWARSYSCEN SAN DIEGO CA | 2 |
|  |  |  | M | (2) Change references to intranet address from nosc.mil to spawar.navy.mil |  |

TABLE OF CONTENTS

1. INTRODUCTION

1.1 PURPOSE

1.2 BACKGROUND

1.3 ENTRY CRITERIA

1.4 SCOPE

1.5 TAILORING GUIDELINES

1.6 DOCUMENT OVERVIEW

1.7 REFERENCES

2. ESTABLISH SQA ORGANIZATION

3. SELECT SQA TASKS

3.1 SQA OF SOFTWARE PRODUCTS, TOOLS, AND FACILITIES

3.1.1 Task:   Review Software Products

3.1.2 Task:  Evaluate Software Tools

3.1.3 Task:  Evaluate Facilities

3.2 SOFTWARE PROCESS AUDITS

3.2.1 Task:  Evaluate Software Products Review Process

3.2.2 Task:  Evaluate Project Planning and Oversight Process

3.2.3 Task:  Evaluate System Requirements Analysis Process

3.2.4 Task:  Evaluate System Design Process

3.2.5 Task:  Evaluate Software Requirements Analysis Process

3.2.6 Task:  Evaluate Software Design Process

3.2.7 Task:  Evaluate Software Implementation and Unit Testing Process

3.2.8 Task:  Evaluate Unit Integration and Testing, CSCI Qualification Testing, CSCI/HWCI Integration and Testing, and System Qualification Testing

3.2.9 Task:  Evaluate  End-item Delivery Process

3.2.10 Task:  Evaluate the Corrective Action Process

3.2.11 Task:  Media Certification

3.2.12 Task:  Nondeliverable Software Certification

3.2.13 Task:  Evaluate Storage and Handling Process

3.2.14 Task:  Evaluate Subcontractor Control

3.2.15 Task:  Evaluate Deviations and Waivers Process

3.2.16 Task:  Evaluate Configuration Management Process

3.2.17 Task:  Evaluate Software Development Library Control Process

3.2.18 Task:  Evaluate Non-developmental Software Process

3.2.19 Task:  Perform Configuration Audits

3.2.20 Task:  Verifying Implementation of Requirements Management KPA

3.2.21 Task:  Verifying Implementation of Software Project Planning KPA

3.2.22 Task: Verifying Implementation of Software Project Tracking and Oversight KPA

3.2.23 Task: Verifying Implementation of Software Subcontract Management KPA

3.2.24 Task: Verifying Implementation of Software Configuration Management KPA

3.2.25 Task: Verifying Implementation of Organization Process Definition KPA

3.2.26 Task: Verifying Implementation of Integrated Software Management KPA

3.2.27 Task: Verifying Implementation of Software Product Engineering KPA

3.2.28 Task: Verifying Implementation of Intergroup Coordination KPA

3.2.29 Task: Verifying Implementation of Peer Reviews KPA

3.3 TECHNICAL AND MANAGEMENT REVIEWS

3.3.1 Task:  Participate in Technical Reviews

3.3.1.1 Task:  Report on Technical Review

3.3.1.2 Task:  Report Technical Review Metrics

3.3.2 Task:  Participate In Management Reviews

3.4 SQA REPORTING

3.4.1 Task - Prepare Software Product Evaluation Records

3.4.2 Task - Prepare Software Process Audit Reports

3.5 SQA METRICS

3.5.1 Task:  Collect and Report Software Product Evaluation Metrics

3.5.2 Task:  Collect and Report Software Product Quality Metrics

3.5.3 Task - Collect and Report Software Process Audit Metrics

4. CREATE/MAINTAIN SQA  PLAN

4.1 SAMPLE PROCEDURES TO CREATE AND MAINTAIN A PROJECT SQA PLAN

5. IMPLEMENT SQA PLAN

6. CREATE/MAINTAIN SQA PROCEDURES

7. IDENTIFY SQA TRAINING

8. IDENTIFY/SELECT SQA TOOLS

8.1 SQA TOOLS SELECTION PROCESS

9. IMPROVE PROJECT SQA  PROCESSES

10. TERMS, DEFINITIONS AND ACRONYMS

10.1 TERMS AND DEFINITIONS

10.2 ACRONYMS

List of Tables

Table 1.  Measurements for SQA

List of figures

Figure 1. SQA Process Overview

Figure 2.  Example SQA Organization

Figure 3.  Select SQA Tasks Overview

Figure 4.  Sample Software Tool Evaluation Form

Figure 5.  Sample Software Tool Evaluation Form

Figure 6.  Software Process Audits Overview

Figure 7.  Process Audit Report Form

Figure 8.  Sample SRS Evaluation Metric

Figure 9.  Sample Process Audit Metric

Figure 10. Sample Procedures to Create and Maintain a Project SQAP

Figure 11. Sample Procedures to Create and Maintain a Project SQAP (continued)

# INTRODUCTION

## PURPOSE

The purpose of this document is to assist Space and Naval Warfare Systems Center, San Diego, CA (SPAWARSYSCEN SAN DIEGO CA) projects in establishing a Software Quality Assurance (SQA) function.  This SQA process describes eight activities.  They are:

- Establish SQA Organization

- Select SQA Tasks

- Create/Maintain SQA Plan

- Implement SQA Plan

- Create/Maintain SQA Procedures

- Identify SQA Training

- Identify/Select SQA Tools

- Improve Project SQA Processes.

Figure 1 is an overview of the SQA process activities.

## BACKGROUND

This document provides the activities for achieving compliance with the SQA Key Process Area (KPA) at the “Repeatable” level on the Software Engineering Institute’s (SEI) Software Capability Maturity Model (SW-CMM) and meeting Department of Defense (DOD) and industry guidelines.  This document covers the activities for implementing SQA for a project.

## ENTRY CRITERIA

There are three entrance criteria for following this process:

- Program and project management commitment to the SPAWARSYSCEN SAN DIEGO CA SQA Policy.

- Quality Factors have been identified.

- Quality Program is defined in the Software Development Plan (SDP) and/or Statement of Work (SOW).

SPAWARSYSCEN SAN DIEGO CA SQA Policy is our written organizational policy for implementing SQA to provide management with appropriate visibility into the process being used by the software project and of the products being built.   The SQA Policy is based on the SQA KPA of the SEI SW-CMM. Program and project management must commit to this policy and ensure it is followed.

Quality Factors are characteristics which a software product exhibits that reflect the degree of acceptability of the product to the user.  Identifying quality factors is a software engineering activity that involves identifying and building quality factors in the software program which can be measured and evaluated.  See references 3, 4, and 5 for assistance in identifying quality factors.

A Quality Program is defined by the processes that will be used in developing software. Software is, or should be, developed and maintained in accordance with a defined process.  A software development or maintenance process consists of the activities that must be performed, the specific products that result from these activities, and the reviews and audits that are held during, and at the conclusion of, these activities.   The SDP is the guide that should control all of the software developer’s activities and is the vehicle by which the developer tells the acquirer how they will do the job.  The SDP is tailored specifically for the project, but should include proven methods and procedures from past successful software development projects.  The quality program is the checks and balances in the software development process or methodology that will ensure that quality software is being built.  The quality program is defined in the project SDP and/or SOW.  MIL-STD-498, Software Development and Documentation, is the software development standard referenced in this document.

## SCOPE

This process can be applied to a specific project within SPAWARSYSCEN SAN DIEGO CA or an outside organization.

## TAILORING GUIDELINES

Projects that find it necessary to provide more in-depth details to their SQA processes may add additional requirements to this process.

## DOCUMENT OVERVIEW

Section 1, Introduction, provides the purpose, background, entry criteria to this process, scope, tailoring guidelines, and references.

Section 2, Establish SQA Organization, describes the measure of independence for establishing an SQA organization.

Section 3, Select SQA Tasks, provides a list of  SQA tasks that can or should be performed by SQA on a project.  This process activity involves program or project management to agree with the SQA representative on the tasks that SQA will perform.  The selected SQA  tasks are an input to the SQAP.

Section 4, Create/Maintain SQA Plan, describes the activity for documenting what SQA plans to do to support the project by identifying all the SQA activities that will be performed, getting project buy-in (all project participants review the plan), getting program/project approval of the plan, placing the plan under configuration control,  and how process improvement may affect a change to the SQA Plan (SQAP) by requiring approval of a change/update to the plan.  The SQAP clearly defines the products to be reviewed by SQA and the project processes to be audited by SQA.

Section 5, Implement SQA Plan, is the project’s implementation of the approved SQAP.

Section 6, Create/Maintain SQA Procedures, describes the activity for  documenting how SQA will perform a task, such as, SQA procedural steps to audit a process or evaluate a software product.  The goal of this process activity is to show  “repeatability” of performing a specific task.

Section 7, Identify SQA Training,  describes the activity of SQA personnel identifying any SQA training that may be required to perform the SQA tasks.  Project specific requirements will dictate what training SQA needs to adequately perform the SQA function.

Section 8, Identify/Select SQA Tools, defines the steps in selecting a SQA tool to support  an SQA function or functions.

Section 9, Improve Project SQA Processes, describes the activity of project SQA personnel to review existing project SQA processes and report on areas for improvement and identify processes that need to be defined.

Section 10, is a list of terms, definitions, and acronyms.

## REFERENCES

The following documents were used to develop this process document:

- CMU/SEI-93-TR-24, Capability Maturity Model for Software, Version 1.1, February 1993

- SPAWARSYSCEN SAN DIEGO CA Software Quality Assurance Policy

- Specifying Software Quality Requirements with Metrics, Steven E. Keller and Lawrence G. Kahn, Dynamics Research Corporation, and Roger B. Panara, Rome Air Development Center

- A Method for Tailoring the Information Content of a Software Process Model, Dr. Sharon Perkins and Mark B. Arend, Society for Software Quality Journal, November 1994

- SPAWARSYSCEN SAN DIEGO CA Requirements Management Guidebook

- SPAWARSYSCEN SAN DIEGO CA Formal Inspection Process

- ANSI/IEEE Std 730-1989, Standard for Software Quality Assurance Plans

- IEEE Std 1298/A3563.1, Software Quality Management System

- DOD-STD-2168, Defense System Software Quality Program

- Data Item Description (DID) DI-QCIC-80572, Software Quality Program Plan

- MIL-HDBK-286, A guide for DOD-STD-2168

- MIL-STD-498, Software Development and Documentation

- Process Development Guidelines for SPAWARSYSCEN SAN DIEGO CA Software Engineering Process Documents, Version 2.0, 12/11/96

- MIL-STD-1521B, Technical Reviews and Audits for System, Equipments, and Computer Software (audit portion superseded by MIL-STD-973)

- MIL-STD-973, Configuration Management

Figure 1. SQA Process Overview

# ESTABLISH SQA ORGANIZATION

Many sources of good software practice call for a measure of independence for the SQA group.  This independence provides a key strength to SQA; that is, SQA has the freedom, if the quality of the product is being jeopardized, to report this possibility directly above the level of the project.  While in practice this rarely occurs (for almost all problems are correctly addressed at the project level), the fact that the SQA group can go above the project level gives it the ability to keep many of these problems at the project level.

The SQA function may be assigned to one person or to an organization, or it may be assigned to multiple persons or organizations.   If an Independent Verification and Validation (IV&V) function has been established for the project, the SQA organizational group may be in the reporting line for IV&V information.

Figure 2 shows an example SQA organization with relation to the project organization.  The project SQA organization, including roles and responsibilities,  is documented in the project SQAP.  The organization chart called for in the SQAP, SDP, SCMP, and other plans controlling the project’s execution should be consistent.

Figure 2.  Example SQA Organization

# SELECT SQA TASKS

In implementing a Quality Program, program and project management should include SQA activities to assure that the software development processes or methodology defined in the SDP are followed.  SQA’s role will:

- identify and help mitigate project risk,

- provide senior management with visibility into development activities, and

- provide feedback into the effectiveness of continuous improvement in the software development process.

This process activity requires the person tasked to perform SQA and program or project management to identify and plan the SQA tasks to be performed.  The objective is to select those tasks that will provide an appropriate level of SQA on the project.    Identifying any SQA tasks requires consideration and compatibility with the project’s SDP, SCMP, and other plans controlling the project’s execution.  SQA tasks are documented in the project SQAP.

Figure 3  provides an overview of the SQA Process Activity “Select SQA Tasks”.  The list of SQA tasks is not intended to be an inclusive list of all SQA tasks.

Figure 3.  Select SQA Tasks Overview

## SQA Of Software Products, Tools, And Facilities

An SQA review of software products is evaluating a software product against a prescribed standard or guideline and reporting errors, omissions, and additions for corrective action. The SQA evaluation of tools used by the project  may be necessary to ensure that the project is using the appropriate technology for developing the software, using the tool for its intended purpose, and using the tool by properly trained project personnel.  The SQA evaluation of project facilities helps management to consider such things as future purchases, expansion of laboratory space, or possibly sharing resources with another project’s facility.

### Task:   Review Software Products

SQA reviews of software products shall be applied, but not limited, to the following:  development plans, standards, procedures, tools, and processes; software requirements; software design; code; control mechanisms for tracking the design, code, database, manuals, and test information (testing of software units; software integration tests; software performance tests).

The project’s SDP identifies all software products to be developed and evaluated and should include the standards or guidelines to be followed.  As required, SQA should assist the project in identifying the standards or guidelines to be followed in developing the software product.  Additionally, the project SDP should identify the review process of the software products.  The project SQAP  should list the software products to be evaluated by SQA and identify the review process to be followed.

The following provides examples of two types of software product reviews:

- Informal Walkthrough (can also be called Non-Author Review, Technical Review) - the item being reviewed is presented by the primary author in an informal setting with his or her peers.  Defects noted are recorded and the author is obligated to address or fix them.

- Formal Inspections - the item being reviewed is formally presented and discussed in a group meeting conducted by a facilitator rather than the item’s primary author.  Errors discovered are rigorously recorded, categorized, and analyzed for trends. SPAWARSYSCEN SAN DIEGO CA’s Formal Inspection Process is a defined, structured, and disciplined method for finding defects in any software work product at any stage of its development or maintenance.  See reference 6 in section 1.7.

SQA should report the results of the software product evaluation using the prescribed format and report the metric for performing this task.

### Task:  Evaluate Software Tools

SQA shall conduct evaluations of tools, both existing and planned, used for software development and support.  The tools are evaluated for adequacy by assessing whether they perform the functions for which the tools are intended and for applicability by assessing whether the tools capabilities are needed for the software development or support.  Planned tools are evaluated for feasibility by assessing whether they can be developed with the techniques and computer resources available or  by procurement.  Figure 4  provides an example format for reporting the results of a software tool evaluation.  The metric for performing this task should be reported.

SOFTWARE TOOL EVALUATION

SQA:_________________________			DATE OF EVALUATION:________

Software Tool Evaluated:

Methods or criteria used in the evaluation:

Evaluation Results:

Recommended Corrective Actions

Corrective Action Taken

Figure 4.  Sample Software Tool Evaluation Form

### Task:  Evaluate Facilities

SQA shall evaluate facilities, both existing and planned, for adequacy by assessing whether they provide the needed equipment and space used for software development and support. Figure 5  provides an example format for reporting the results of the project’s software development and support facilities.  The metric for performing this task should be reported.

PROJECT FACILITIES  EVALUATION

SQA:_________________________			DATE OF EVALUATION:________

Facility Evaluated (Equipment, User/Test/Library Space):

Methods or criteria used in the evaluation:

Evaluation Results:

Recommended Corrective Actions

Corrective Action Taken

Figure 5.  Sample Software Tool Evaluation Form

## Software Process Audits

Audits of compliance for prescribed organizational and project processes are a critical component of software quality.  Software Process Audits are conducted to ensure that the process defined by the organization and the SDP are followed as the project progresses.  These audits take the form of selected reviews of individual project activities to determine that the project conducts each activity.

Process improvement requires the process used on the project be periodically assessed to determine their suitability and effectiveness.  Based on these assessments, SQA should identify any necessary and beneficial improvements to the process, and identify those improvements as proposed updates to the SDP, SCMP, SQAP, or other plans controlling the project’s execution, and if approved, implement the improvements on the project.  The following are guidelines when performing a software process audit by SQA:

- Means of determining the scope of the audit - SQA should follow a defined procedure in conducting the audit to ensure that the right steps are identified and are being reviewed to provide the maximum benefit.  The SQA Audit Procedure should be made available to project personnel.  This will communicate SQA’s scope and purpose of conducting a specific software process audit, e.g., SQA will audit the project’s peer review process for code, unit test cases, and unit test procedures.

- Process compliance - For those areas where the process is being followed, SQA should favorably report  the effectiveness of the process activity in meeting activity and project goals, and recommended action to be taken, if any (change the process if the process is not robust enough).

- Process noncompliance - For those areas where the process is not being followed, SQA should report noncompliance, its impact on the project, and recommended action be taken by the project team and management.

A sample format for a Process Audit Report is found in Section 2.4, SQA Reporting.  The metric for performing this activity should also be reported.

The following tasks descriptions include phase specific activities of MIL-STD-498 and verifying implementation of the Key Process Areas (KPAs) of the SW-CMM.  Figure 6  provides an expanded overview of the SQA Task “Software Process Audits”.

Figure 6.  Software Process Audits Overview

### Task:  Evaluate Software Products Review Process

SQA evaluation of the Software Products Review process checks that software products that are ready for review are reviewed, review results are reported and issues or problems reported are resolved in accordance with the project’s SDP and procedures.   Software products may include representations of information other than traditional hard-copy documents.

SQA should report the results of evaluating the software products review process using the Process Audit Report form and report the metric for performing this task.

### Task:  Evaluate Project Planning and Oversight Process

Project planning and oversight requires project management to develop and document plans for the following:

Software Development Planning - A plan for conducting the activities required by the software development standard, e.g., DOD-STD-2167A, MIL-STD-498, and by other software-related requirements in the contract, Memorandum of Agreement, Memorandum of Understanding, etc.  Planning is documented in the SDP which identifies events, reviews, and audits to be performed on the project based on the appropriate point in the software development lifecycle.

CSCI Test Planning - A plan for conducting CSCI qualification testing.  Planning is documented in the Software Test Plan.

System Test Planning - A plan for conducting system qualification testing.  For software systems, planning is included in the Software Test Plan.

Software Installation Planning - A plan for performing software installation and training at the user sites.  Planning is documented in the Software Installation Plan.

Software Transition Planning - A plan for identifying all software development resources that will be needed by the support agency, e.g., Software Support Activity, to fulfill the support concept, e.g., maintenance.  Planning for this involves identifying the resources and describing the approach to be followed to transition deliverable items to the support agency.  Planning is documented in the Software Transition Plan.

SQA ensures that the project conduct the relevant activities stated in those project plans.  Any changes to those plans would require update and approval by project management.   For planning documents to be developed, SQA would identify standards or guidelines, or an appropriate Data Item Description (DID) and assist with the tailoring of the standard, guideline, or DID to meet the project’s needs.

### Task:  Evaluate System Requirements Analysis Process

Requirements analysis establishes a common understanding of the customer’s requirements between the customer and the software project team.  An agreement with the customer on the requirements for the software project is established and maintained.  This agreement is known as allocating system requirements to software and hardware.  System requirements are documented, such as in the Operational Concept Description (OCD), System/Subsystem Specification (SSS), and Interface Requirements Specification (IRS).

SQA shall perform the following:

- Ensure that the correct participants are involved in the requirements definition and allocation process to identify all user needs.

- Ensure that requirements are reviewed to determine if they are feasible to implement, clearly stated, and consistent.

- Ensure that changes to allocated requirements, work products, and activities are identified, reviewed, and tracked to closure.

- Ensure that project personnel involved in the requirements definition and allocation process are trained in the necessary procedures and standards applicable to their area of responsibility in order to do the job correctly.

- Ensure that the commitments resulting from allocated requirements are agreed upon by negotiated with the affected groups.

- Verify that commitments are documented, communicated, reviewed, and accepted.

- Ensure that allocated requirements identified as having potential problems are reviewed with the group responsible for analyzing system requirements and documents, and that necessary changes are made.

- Verify that the prescribed processes for defining, documenting, and allocating requirements are followed and documented.

- Confirm that a CM process is in place to control and manage the baseline.

- Verify that requirements are documented, managed, controlled, and traced (preferably via a matrix).

- Verify that the agreed upon requirements are addressed in the SDP.

### Task:  Evaluate System Design Process

System-wide design decisions are decisions about the system’s behavioral design and other decisions affecting the selection and design of system components.  System architectural design is organizing a system into subsystems, organizing a subsystem into Hardware Configuration Items (HWCIs), Computer Software Configuration Items (CSCIs), and manual operations, or other variations as appropriate.  System design is documented, such as in the System/Subsystem Design Description (SSDD) and Interface Design Description (IDD).

SQA shall perform the following:

- Ensure that lifecycle documents and the traceability matrix are prepared and kept current and consistent.

- Verify that relevant lifecycle documents are updated and based on approved requirements change.

- Ensure that design walkthroughs (peer reviews) evaluate compliance of the design to the requirements, identify defects in the design, and alternatives are evaluated and reported.

- Participate in a sampled set of design walkthroughs and verify all walkthroughs are conducted.

- Identify defects, verify resolution for previously identified defects, and ensure change control integrity.

- Selectively review and audit the content of system design documents.

- Identify lack of compliance with standards and determine corrective actions.

- Determine whether the requirements and accompanying design and tools conform to standards, and whether waivers are needed prior to continuing software development.

- Review demonstration prototypes for compliance with requirements and standards.

- Ensure that the demonstration conforms to standards and procedures.

- Review the status of design milestones.

### Task:  Evaluate Software Requirements Analysis Process

Software Requirements Analysis is defining and recording the software requirements to be met by each CSCI, the methods to be used to ensure that each requirement has been met, and the traceability between the CSCI requirements and system requirements.  Software requirements are documented, such as in the Software Requirements Specification (SRS) and IRS.

SQA shall perform the following:

- Ensure that the software requirements definition and analysis process and associated requirements reviews are conducted in accordance with the standards and procedures established by the project and as described in the SDP.

- Ensure that action items resulting from reviews of the software requirements analysis are resolved in accordance with these standards and procedures.

### Task:  Evaluate Software Design Process

Preliminary design activity determines the overall structure of the software to be built.  Based on the requirements identified in the previous phase, the software is partitioned into modules, and the function(s) of each module and relationships among these modules are defined.

Detailed design is to define and complete the detailed design of software logically to satisfy allocated requirements.  The level of detail of this design must be such that the coding of the computer program can be accomplished by someone other than the original designer.  Software design is documented, such as in the Software Design Description (SDD), Database Design Description (DBDD), and Interface Design Description (IDD).

SQA shall perform the following:

- Ensure that the software design process and associated design reviews are conducted in accordance with standards and procedures established by the project and as described in the SDP.

- Ensure that action items resulting from reviews of the design are resolved in accordance with these standards and procedures.

- Evaluate the method used for tracking and documenting the development of a software unit in order to determine the method's utility as a management tool for assessing software unit development progress.  Example criteria to be applied for the evaluation are the inclusion of schedule information, results of audits, and an indication of internal review and approval of what was reviewed.

- Ensure that the method, such as the Software Development File (SDF) or Unit Development Folder (UDF) used for tracking and documenting the development of a software unit is implemented and is kept current.

### Task:  Evaluate Software Implementation and Unit Testing Process

Software implementation or coding is the point in the software development cycle at which the design is implemented.  This process includes unit testing of the software.

SQA shall perform the following:

- Ensure that the coding process, associated code reviews, and software unit testing are conducted in conformance with the standards and procedures.

- Ensure that action items resulting from reviews of the code are resolved in accordance with these standards and procedures established by the project and as described in the SDP.

- Ensure that the SDF/UDF used for tracking and documenting the development of a software unit is implemented and is kept current.

### Task:  Evaluate Unit Integration and Testing, CSCI Qualification Testing, CSCI/HWCI Integration and Testing, and System Qualification Testing

Software integration and test activities combine individually developed components together in the developing environment to ensure components work together to complete the software and system functionality.  For joint hardware and software development, integration requires close synchronization of hardware and software to meet designated integration and test milestones.

In the integration and test phase of the development lifecycle, the testing focus shifts from an individual component correctness to the proper operation of interfaces between components, the flow of information through the system, and the satisfaction of system requirements.

SQA shall perform the following:

- Ensure that software test activities are identified, test environments have been defined, and guidelines for testing have been designed.  SQA will verify the software integration process, software integration testing activities and the software performance testing activities are being performed in accordance with the SDP, the software design, the plan for software testing, and established software standards and procedures.

- Ensure any transfer of code to personnel performing software integration testing or software performance testing is being accomplished in accordance with established software standards and procedures.

- Ensure as many of the software integration tests as necessary and all of the software performance tests are witnessed to ensure that the approved test procedures are being followed, that accurate records of test results are being kept, that all discrepancies discovered during the tests are being properly reported, that test results are being analyzed, and the associated test reports are completed.

- Ensure the corrective action process effectively allows discrepancies discovered during software integration and performance tests are identified, analyzed, and corrected; software unit tests, and software integration tests are re-executed as necessary to validate corrections made to the code; and the software unit's design, code, and test is updated based on the results of software integration testing, software performance testing, and corrective action process.

- Ensure the software performance tests produce results that will permit determination of performance parameters of the software.

- Ensure that the responsibility for testing and for reporting on results has been assigned to a specific organizational element.

- Ensure that procedures are established for monitoring testing.

- Review the Software Test Plan and Software Test Procedures for compliance with requirements and standards.

- Ensure that the software is tested.

- Monitor test activities, witness tests, and certify test results.

- Ensure that requirements have been established for the certification or calibration of all support software or hardware used during tests.

### Task:  Evaluate  End-item Delivery Process

This activity is applicable for those projects providing a one-time delivery of a product and may also be interpreted as required deliveries for a specified time period or time frame.

SQA shall evaluate the activities in preparation for end-item delivery to ensure that program or project  requirement, if any, for functional and physical audits of the end-item products are being satisfied.  In some cases, SQA should be allowed to prohibit delivery of certain items, such as documentation, code, or a system, if the project fails to meet program or project requirements or standards.

### Task:  Evaluate the Corrective Action Process

The corrective action process describes the steps for (1) problem identification and correction occurring during software development to ensure early detection of actual or potential problems, (2) reporting of the problem to the proper authority, (3) analysis of the problem in order to propose corrective measures, (4) timely and complete corrective action, and (5) the recording and follow-up of each problem's status.  Problems in this context include documentation errors, software errors, and noncompliance with standards and procedures.

SQA shall perform the following:

- Periodically review the corrective action processes and their results against the SCMP in order to assess the effectiveness of the correction action process.

- Perform periodic analysis of all reported problems to identify trends that may disclose generic problem areas.  These analyses shall include the study of the causes, magnitude of impact, frequency of occurrence, and preventive measures.

### Task:  Media Certification

SQA shall certify that the media containing the source code and the media containing the object code which are delivered to the procuring agency correspond to one another.  SQA shall certify also that the software version represented by this media matches that on which software performance testing was performed, or correctly represents an authorized update of the code, as applicable.

SQA reports, together with the corrective action records, software test reports, and software product evaluation records can constitute the required evidence for certification.

### Task:  Nondeliverable Software Certification

The project may use non-deliverable software in the development of deliverable software as long as the operation and support of the deliverable software, after delivery to the acquirer, does not depend on the non-deliverable software or provision is made to ensure that the acquirer has or can obtain the same software.   SQA shall certify that the use of non-deliverable software meets the above criteria, that is, deliverable software is not dependent on non-deliverable software to execute, or verify that the acquirer can obtain the same software.  SQA shall certify that all non-deliverable software used on the project performs its intended functions.

SQA reports, together with the corrective action records, software test reports, and software product evaluation records can constitute the required evidence to verify that the software performs its intended functions.

### Task:  Evaluate Storage and Handling Process

SQA shall verify that there is an established plan, methodology, or set of procedures for storage and handling of the media.  SQA shall evaluate the storage of the software product and documentation to ensure that storage areas for paper products or media are free from adverse environmental effects such as high humidity, magnetic forces, and dust.

### Task:  Evaluate Subcontractor Control

SQA shall be responsible for ensuring that the quality of all software products from subcontractors conforms to the contract requirements and that the subcontractor's CM plan and procedures are being followed.

### Task:  Evaluate Deviations and Waivers Process

SQA shall assist program or project management, with requests for deviations and waivers if required, and verify that the deviation or waiver request is processed in accordance with the project’s SCMP and approved by the approving agency.

### Task:  Evaluate Configuration Management Process

Configuration Management is the discipline that applies technical and administrative direction and surveillance to  (1)  Identify and document the functional and physical characteristics of CIs, (2) Control the changes to CIs and their related documentation, (3) Record and report information needed to manage CSCIs effectively, including the status of proposed changes and the implementation status of approved changes, and (4) Audit the CIs to verify conformance to specifications, interface control documents, and other requirements.

SQA shall evaluate the following:

- Ensure that configuration identification of documents, code, and computer data have established standards for titling, naming, and describing change status.

- Ensure that baseline management of changes to the developmental baseline (including documents, code and computer data) are identified, reviewed, implemented, and incorporated in accordance with established procedures.

- Ensure configuration control of changes to baseline documents and software are being managed in accordance with CM requirements specified in the SDP.

- Ensure configuration status accounting reports are prepared at established times, are prepared in accordance with established procedures, and report the status of items that are significant with respect to the management of the configuration of the software product and documentation.

- Ensure that the personnel assigned to participate in the configuration audits comply with the SCMP.

- Ensure for document control that only approved, up-to-date documentation is being used by project personnel, and that the document distribution process results in receipt of correct documentation.

- Ensure that the program  support library is the single place of storage for the baseline version of all software and ensure that the identification of all software includes the software name and a unique version identifier.  The evaluation shall also determine that control of access to software products is being properly exercised and that unauthorized changes to master files cannot occur.

### Task:  Evaluate Software Development Library Control Process

The SDL functions as the main control point for software CM.  A SDL contains all units of code developed for evolving project CSCIs, as well as carefully identified listings, patches, errata, CSCI and system magnetic tapes and disk packs, and job control streams for operating or building software systems.  The SDL also contains previous versions of the operational software system in the form of magnetic tapes or disk packs.

SQA shall perform the following:

- Ensure the establishment of the SDL and procedures to govern its operation.

- Ensure that documentation and computer program materials are approved and placed under library control.

- Ensure the establishment of formal release procedures for CM approved documentation and software versions.

- Ensure that  library controls prevent unauthorized changes to the controlled software and ensure the incorporation of all approved changes.

### Task:  Evaluate Non-developmental Software Process

Non-Developmental Software (NDS) is software that is provided by the contractor, the Government, or a third party.  NDS may be referred to as reusable software, Government-furnished software, or commercially available software depending on it source.  SQA shall verify that non-developmental software performs its intended functions.

### Task:  Perform Configuration Audits

SQA may be required to perform or assist in a formal configuration audit in accordance with the project SCMP.  A configuration audit is a formal examination of a CSCI.  Two types of configuration audits exist:  The Function Configuration Audit (FCA) and the Physical Configuration Audit (PCA).  (MIL-STD-973 provides further details of these two audits.)

### Task:  Verifying Implementation of Requirements Management KPA

The purpose of Requirements Management is to establish a common understanding of the customer’s requirements between the customer and the software project.

The SQA group reviews and/or audits the activities and work products for managing the allocated requirements and reports the results.

### Task:  Verifying Implementation of Software Project Planning KPA

The purpose of Software Project Planning is to establish reasonable plans for performing the software engineering and for managing the software project.

The SQA group reviews and/or audits the activities and work products for software project planning and report the results.

### Task: Verifying Implementation of Software Project Tracking and Oversight KPA

The purpose of Software Project Tracking and Oversight is to establish adequate visibility into actual progress so that management can take effective actions when the software project’s performance deviates significantly from the software plans.

The SQA group reviews and/or audits the activities and work products for software project tracking and oversight and report the results.

### Task: Verifying Implementation of Software Subcontract Management KPA

The purpose of Software Subcontract Management is to select qualified software subcontractors and manage them effectively.

The SQA group reviews and/or audits the activities and work products for software subcontract  and report the results.

### Task: Verifying Implementation of Software Configuration Management KPA

The purpose of Software Configuration Management is to establish and maintain the integrity of the products of the software project throughout the project’s software life cycle.

The SQA group reviews and/or audits the activities and work products for software configuration management and report the results.

### Task: Verifying Implementation of Organization Process Definition KPA

The purpose of Organization Process Definition is to develop and maintain a usable set of software process assets that improve process performance across the projects and provide a basis for cumulative, long-term benefits to the organization.

The SQA group reviews and/or audits the organization’s activities and work products for developing and maintaining the organization’s standard software process and related process assets and report the results.

### Task: Verifying Implementation of Integrated Software Management KPA

The purpose of Integrated Software Management is to integrate the software engineering and management activities into a coherent, defined software process that is tailored from the organization’s standard software process and related process assets, which are described in Organization Process Definition.

The SQA group reviews and/or audits the activities and work products for managing the software project and report the results.

### Task: Verifying Implementation of Software Product Engineering KPA

The purpose of Software Product Engineering is to consistently perform a well-defined engineering process that integrates all the software engineering activities to produce correct, consistent software products effectively and efficiently.

The SQA group reviews and/or audits the activities and work products for software product engineering and report the results.

### Task: Verifying Implementation of Intergroup Coordination KPA

The purpose of Intergroup Coordination is to establish a means for the software engineering group to participate actively with the other engineering groups so the project is better able to satisfy the customer’s needs effectively and efficiently.

The SQA group reviews and/or audits the activities and work products for intergroup coordination and report the results.

### Task: Verifying Implementation of Peer Reviews KPA

The purpose of Peer Reviews is to remove defects from the software work products early.

The SQA group reviews and/or audits the activities and work products for peer reviews and report the results.

## Technical And Management Reviews

Technical reviews conducted by the project team are based on the key products produced during the life of the project. Management reviews are held to examine and discuss project status, software products, and/or project issues.  Conducting a technical and management review depend on the major milestones, the selected program strategies and development methodologies, and the discretion of senior management and the project manager.  An SQA function provides input to ensure that reviews identified are adequate for the project.  Additionally, SQA participates in reviews and reports it’s review results and metrics.

### Task:  Participate in Technical Reviews

A primary component of engineering quality into software is the conduct of technical reviews of software products, both deliverable and nondeliverable.  Participants of a technical review include persons with technical knowledge of the software products to be reviewed.  The reviews focus on in-progress and final software products rather than the materials generated especially for the review.  The SQA function assures that they are accomplished and selectively attends them in accordance with approved sampling techniques.  The type and scope of technical reviews depends heavily on the size, scope, risk and criticality of the software project.  Technical reviews help increase proficiency through on-the-job-training and permit a uniform method for reviewing the work and its status.  Objectives of this type of review are:

- Review evolving software products. Review and demonstrate proposed technical solutions.  Provide insight and obtain feedback on the technical effort.  Surface and resolve technical issues.

- Appendix D of MIL-STD-498, Software Product Evaluations, identifies criteria to be used for an evaluation and contains a defaults set of definitions for the evaluation criteria.  MIL-STD-498 also identifies 3 conditions in using Appendix D:  (1) requirements may be tailored, (2) “approved” alternate criteria or definitions may be used, and (3) if the development of a software product has been tailored out, the requirement to evaluate that product does not apply.

- Review project status.  Surface near- and long-term risk regarding technical, costs, and schedule issues.

- Arrive at agreed-upon mitigation strategies for identified risks, within the authority of those present.

- Identify risks and issues to be raised at joint management reviews.

- Ensure on-going communications between acquirer and developer technical personnel.

A Technical Review involves an item to be reviewed is distributed to the group prior to the review meeting, and the review centers on discussing reviewers comments.  These usually occur at the conclusion of each development cycle phase and center on whether the product should proceed to the next phase of development.    MIL-STD-1521B, Technical Reviews and Audits for Systems, Equipments, and Computer Software, defines the following Technical Reviews:

System Requirements Review (SRR) - the objective is to ascertain the adequacy of the developer’s efforts in defining system requirements.

System Design Review (SDR) - the objective is to evaluate the optimization, correlation, completeness, and risks associated with the allocated technical requirements.  Also included is a summary review of the system engineering process which produced the allocated technical requirements and of the engineering planning for the next phase of effort.

Software Specification Review (SSR) - the objective is to review the finalized Computer Software configuration Item (CSCI) requirements and operational concept.  A successful SSR shows that the SRS, IRS, and Operational Concept Document form a satisfactory basis for proceeding into preliminary software design.

Software Preliminary Design Review (PDR) - the objective is to evaluate the progress, consistency, and technical adequacy of the selected top-level design and test approach, compatibility between software requirements and preliminary design, and the preliminary version of the operation and support documents.

Software Critical Design Review (CDR) - the objective is to determine acceptability of the detailed design, performance, and test characteristics of the design solution, and on the adequacy of the operation and support documents.

Software Test Readiness Review (TRR) - the objective is to determine whether the software test procedures are complete and to assure that the developer is prepared for formal CSCI testing.

Formal Qualification Review (FQR) - the test, inspection, or analytical process by which a group of configuration items comprising the system are verified to have met specific program or project management performance requirements.

Production Readiness Review (PRR) - the objective is to determine the status of completion of the specific actions which must be satisfactorily accomplished prior to executing a production go-ahead decision.

In each case, the goal is to provide constructive feedback on the review item so that problems can be identified and corrected as early as possible, to verify that the item fully meets its objectives in the overall project plan,  and to ensure that the item complies with established standards.

The choice of which type of review is conducted, which items are reviewed, and the participants for each review should be delineated in the software development processes, project SDP, and project SQAP.  Compliance with the established processes is verified through Software Process Audits.

Technical reviews can be conducted on any component of the software product, if deemed appropriate by the formalized processes, SDP, SQAP, or project staff and project management.  Typical items that are reviewed include requirements specifications, interface specifications, functional descriptions, design specifications, source code, test plans, test data, test cases, test procedures, user documentation, and maintenance manuals. The following are criteria that may apply to a technical review:

(1)  Item completeness - Determine whether the item fully met its intended objectives

(2)  Problem Identification - Identify problems as early as possible in order to correct them before they are compounded in subsequent project phases

(3)  Compliance with standards - Ensure the item complies with established or require standards, or that waivers are sought where it does not meet them

(4)  Risk identification - Identify potential risk areas in the project so risks can be managed and mitigated as the project progresses

(5)  Traceability - Ensure the item is traceable to the appropriate previous phase in the project.  Recording item traceability, through a matrix, is very important to developers and managers.  They use the traceability matrix to verify that the software satisfies its requirements and to provide input to subsequent project activities

#### Task:  Report on Technical Review

Issues or discrepancies with the product must be recorded, managed, and tracked to closure.  In some cases, the item will also need to be reviewed again prior to its acceptance.  In other cases, the items noted from the review will be relatively minor and will not necessitate a second review.  The criterion for making this determination should be included as part of the project SQAP.  The results of a review are utilized by:

- Project Manager - the project manager uses the review results to track action items and discrepancies and as input into the status of the item relative to the overall project.

- SQA - the report provides objective evidence that the review has been conducted.  The reviews allow SQA to focus its activities and resources on those items that have more impact on the process.

- SEPO - the report provides the SEPO with data on the effectiveness of individual process steps through an analysis of review items from projects across the organization.

#### Task:  Report Technical Review Metrics

Various metrics should be collected as part of technical reviews to help determine the effectiveness of the review process itself as well as the process steps that are used to produce the item being reviewed.  These metrics, reported to the project manager and SEPG, should include the amount of time spent by each person involved in the review for preparation and conduct of the review and deficiencies (the number and criticality of deficiencies found).

### Task:  Participate In Management Reviews

SQA’s periodic management review of software project status, progress, problems, and risk will provide an independent assessment of project activities.  Such participation requires that SQA be prepared to provide the following information to management:

Compliance - Identification of the level of compliance of the project with established organizational and project processes.

Problem areas - identification of potential or actual project problem areas based on analysis of technical review results.

Risks - identification of risk based on participation and evaluation of project progress and trouble areas.

The SQA function is integral to the success of the project, and should freely communicate its results to senior management, SEPG, project management and the project team.  SQA can often provide additional support to the project manager during management reviews to emphasize areas for senior management attention.

The method for reporting compliance, problem areas, and risks should be communicated in a documented report or memorandum.  Compliance, problem areas, and risks needs to be followed-up and in some cases tracked to closure.

## SQA Reporting

An important SQA activity is reporting the results of any software product evaluation or software process audit.  SQA should document the results of the activities performed and promptly initiate corrective action or provide certification.  The reporting results are provided to the appropriate program/project personnel.  The following subparagraphs discuss the reporting requirements of SQA software product evaluations and software process audits.

### Task - Prepare Software Product Evaluation Records

For any software product evaluation conducted, evaluation records are required.  The requirements for software product evaluation records are they must be prepared and made available to affected program and project personnel.  As a minimum, evaluations records should include:

- the product evaluated,

- the methods or criteria used in the evaluation,

- the evaluation results,

- the recommended corrective actions, and

- the actual corrective actions taken.

The project SDP would identify all software products to be developed and may reference the Data Item Description (DID) or a project-tailored DID to follow.  See Appendix D, Software Product Evaluations,  of MIL-STD-498, which identifies the software products that are to undergo software product evaluations, identifies the criteria to be used for each evaluation, and contains a default set of definitions for the evaluation criteria.

The format of an evaluation record may be dependent on the process used to perform software product evaluations.  For example, a project may implement SPAWARSYSCEN SAN DIEGO CA’s Formal Inspection (FI) Process as the methodology to use for Peer Reviews to evaluate software products.  The SPAWARSYSCEN SAN DIEGO CA FI process includes the form and format to report defects.  The project SDP would describe the peer review process.  Another example is that a  project evaluating a software product may use the Software Trouble Report form which is an input to the Corrective Action Process.  The Software Configuration Management Plan would describe the Corrective Action Process and the STR format.

SQA’s reporting of software product evaluations should be documented in the SQAP that describes what products will be evaluated by SQA,  how the evaluations will be done (the method or criteria), what format is used to report the evaluation results which would include recommended corrective actions or corrective actions to be taken.  The software products that are to be evaluated is further discussed in the paragraph entitled SQA of Software Products, Tools, and Facilities.

### Task - Prepare Software Process Audit Reports

Each Software Process Audit produces a report that  shows areas in which the process

is being followed correctly and working effectively, is being followed but is not working effectively, and is not being followed.  SQA recommendations may lead to adjustments in the process, or enforcement activities intended to bring the project’s execution in line with established plans and processes.  Figure 7  provides a sample format for a Process Audit Report.

The Software Process Audit report is directed to:

- Senior management - The results of Software Process Audits are used in conjunction with other project status information to guide senior management attention to identify and mitigate project risks at the organizational level.

- SEPG - The SEPG utilizes the process audits results, in conjunction with the results of audits of other projects, to identify process weaknesses and initiate or enhance process improvement in specific areas.  This data becomes part of the process database so that it is available for future project analysis and use.

- Project Manager - The project manager utilizes the report to provide insight into whether there is compliance with the development process and its effectiveness in meeting project goals.  Where necessary and appropriate, the project manager may initiate enforcement activities or initiate change to the established processes using the approved procedures.

PROCESS AUDIT REPORT

TRACKING IDENTIFIER:______

_____________________________________________________________________________________

LEAD AUDITOR:						DATE OF REPORT:

______________________________________________________________________________________

AUDIT TEAM:

______________________________________________________________________________________

PROJECT NAME:

______________________________________________________________________________________

DATE OF AUDIT:

______________________________________________________________________________________

PROCESS/PROCEDURE AUDITED:

______________________________________________________________________________________

AUDIT CHECKLIST USED: (Attach)

______________________________________________________________________________________

AUDIT FINDINGS: (Check one.)

_____ 	Process/Procedure Acceptable

_____ 	Process/Procedure Conditionally Acceptable

(Subject to satisfactory completion of action items listed below)

Conditions noted:

_____	Process/Procedure Unacceptable

(Subject to satisfactory completion of action items listed below)

Conditions noted:

______________________________________________________________________________________

ACTION ITEM (AI):

AI  #  TITLE:                                     ASSIGNED TO:             DUE DATE:   COMP DATE:_______

______________________________________________________________________________________

______________________________________________________________________________________

______________________________________________________________________________________

CORRECTIVE ACTION:

______________________________________________________________________________________

DISPOSITION:	APPROVE    CANCEL    DEFER

Project Manager:							DATE:

______________________________________________________________________________________

AI CLOSURE:

SQA Sign-off:							DATE:

(FILE COMPLETED FORM IN SQA EVALUATION RECORD.)

Figure 7.  Process Audit Report Form

## SQA Metrics

Table 1 provides measurements that are made and used to determine the schedule and cost status of the SQA activities:

Table 1.  Measurements for SQA

| MEASUREMENTS | METRIC TO COLLECT |
| --- | --- |
| SQA Milestone Dates (Planned) | Report plan |
| SQA Milestone Dates (Completed) | Report actual vs. plan |
| SQA Work Scheduled (Planned) | Report plan |
| SQA Work Completed (Actual) | Report actual vs. plan |
| SQA Effort Expended (Planned) | Report # of Hours |
| SQA Effort Expended (Actual) | Report # of Hours |
| SQA Funds Expended (Planned) | Report $ of Person Year |
| SQA Funds Expended (Actual) | Report $ of Person Year |

The following paragraphs provide example task descriptions to collect and report metrics on (1) Software Product Evaluations, (2) Software Product Quality, and (3) Software Process Audits.

### Task:  Collect and Report Software Product Evaluation Metrics

This activity  involves recording the effort involved in SQA performing an evaluation of the software product.  The metric collected and recorded is a person’s effort (hours) for evaluating a software product, including reporting software product evaluation findings.  Recording this metric would show the allocation of SQA time in performing a specific SQA activity.  Figure 8 provides an example of SQA evaluating a requirements specification and reporting on the results:

| Software Product | # of Pages | Hours Used for Evaluating | Hours used for Reporting |
| --- | --- | --- | --- |
| Software Requirements Specification (SRS), Increment 1 | 20 | 3 | 1 |

Figure 8.  Sample SRS Evaluation Metric

### Task:  Collect and Report Software Product Quality Metrics

A metric that could be collected is the number and type of errors reported on a software product evaluation.  SQA would analyze this metric to ensure quality.  For example, if SQA found a high number of requirement or design errors, then root cause analysis would be the recommended action to be taken by the software development team.  Cause analysis would look at why the requirement or design errors were not initially caught by the product reviewers.  An area of investigation would be to look at the process to see if the process is robust enough, were the appropriate reviewers included to evaluate the product, were requirements too ambiguous, etc.

### Task - Collect and Report Software Process Audit Metrics

This activity involves conducting and reporting the hours expended for performing an SQA audit of the project’s software processes.  Figure 9 is a sample process audit metric for SQA evaluating the project’s corrective action process.

| Software Development Process Audited | Hours Used for Audit Preparation | Hours Used for Evaluating | Hours used for Reporting |
| --- | --- | --- | --- |
| Corrective Action Process | 2 | 2 | 1 |

Figure 9.  Sample Process Audit Metric

# CREATE/MAINTAIN SQA  PLAN

This SQA activity details the process for creating and maintaining a project SQAP.  The purpose of the SQAP is to describe how the developer intends to ensure that the software is a product whose quality meets those standards defined by the quality policy.  The SQAP details the quality procedures and techniques to be used.  The objective of the plan is to be able to demonstrate how the developer will ensure that the requirements for a software system are met.  The first major quality assurance task is to determine the quality assurance activities that will be carried out during the execution of the project.  This means that, for each phase, the SQAP must define explicitly how quality assurance activities (such as design reviews and system testing) are to be executed.

As a minimum, the SQAP should address:

- Quality objectives, expressed in measurable terms whenever possible.

- Identification of types of test, verification and validation activities to be carried out on product specification, plans and test specifications together with the methods and tools to be employed.

- Defined entry and exit criteria for each development phase.

- Detailed planning of test verification and validation activities to be carried out, including schedules, resources and approval authorities.

- Specific responsibilities for quality activities such as inspections, reviews and tests,

- configuration management and change control, measurement and reporting, defect control and corrective action.

- Responsibilities and authority of the SQA group.

- Resource requirements for the SQA group (including staff, tools, and facilities).

- Schedule and funding of the project’s SQA group activities.

- The SQA group’s participation in establishing the software development plan, standards, and procedures for the project.

- Evaluations to be performed by the SQA group.

- Audits and reviews to be conducted by the SQA group.

- Project standards and procedures used as the basis for the SQA group’s reviews and audits.

- Procedures for documenting and tracking noncompliance issues to closure.

- Documentation that the SQA group is required to produce.

- Method and frequency of providing feedback to the software engineering group and other software-related groups on SQA activities.

References 7 through 12 in Section 1.7 provide references that may be used in developing a project SQAP.

## Sample Procedures to Create and Maintain a Project SQA Plan

Figure 10  provides a sample procedure for creating and maintaining a project SQAP.

Procedures to Create and Maintain a Project SQA Plan (SQAP)

Version 1.0

2/27/1997

This Procedures details the steps to create and maintain a Project SQAP.

1.  Entry Criteria

Entry criteria is defined as the elements and conditions necessary to be in place to begin a procedure.  The entry criteria for this procedure are:

- SQA Policy

- Project requirements

- Project Software Development Plan (SDP)

- Project products, i.e., specifications, standards and procedures

- SQA activities identified

- SQA tasks assigned

- Responsibility for coordinating and implementing SQA for the project is explicitly assigned

- An SQA person, group or function has a reporting channel to senior management that is independent of all other groups involved with the project

- Adequate resources and budget for software project planning have been identified and allocated

- Members involved in SQA activities are trained or skilled in SQA objectives, procedures, and methods

2.  Controls

Controls are defined as the data that constrains or regulates a process activity.  Controls regulate the transformation of inputs into outputs.  The following are controls for creating and or maintaining an SQAP:

- SQAP guidelines,

- Quality Program Requirements

- SQA Policy

3.  SQAP Review

The SQAP shall be reviewed by all project personnel.  This allows project personnel to submit  comments and feedback on the role, responsibility, resources, and activities delineated in the SQAP .  The SQAP shall be reviewed by following the Formal Inspection Process or by following the informal document review process.

Figure 10. Sample Procedures to Create and Maintain a Project SQAP

4.  SQAP Approval

The approval process of the SQAP shall require program or project management  and Configuration Control Board (CCB) approval.

5.  Configuration Control

The approved SQAP shall be placed under configuration control.  Updates to the plan to reflect current project requirements, processes and practices require review and approval.

6.  Measurements

Staffing levels, labor-hours, and the start and stop dates shall be recorded for developing the SQAP including any updates to the SQAP.

7.  Exit Criteria

Exit criteria is defined as elements and/or conditions necessary to be in place to complete a procedure.  The exit criteria for this process activity is the SQAP is approved and placed under configuration management.

8.  Process Improvement on Creating/Maintaining a Project SQAP Procedure

A review on how closely project personnel follow this procedure to create and maintain a Project SQAP and the areas for improvement shall be provided to those responsible for process improvement.  Efficiencies in the process to generate a SQAP may require an update to this procedure.

Figure 11. Sample Procedures to Create and Maintain a Project SQAP (continued)

# IMPLEMENT SQA PLAN

The purpose of this SQA activity is to perform the SQA function in accordance with the project approved SQAP.

# CREATE/MAINTAIN SQA PROCEDURES

The purpose of this activity is to document  and maintain the procedures that describe how SQA is performed on a project in accordance with the currently approved project SQAP. The goal of this process activity is to show  “repeatability” of performing a specific task. Therefore, a documented procedure should be written for performing any SQA activity.

The SQA Manager is responsible for drafting or directing the development of an SQA procedure, implementing the SQA procedure, and maintaining the SQA procedure to reflect activities performed as described in the project SQAP.

Inputs to creating/maintaining SQA procedures include identified tasks (WBS) and the SQAP.  An output of this activity is a documented SQA procedure.  A documented SQA procedure may be included as an appendix to the SQAP or as a separate stand-alone document from the SQAP.  The author suggests that procedures be separate from the SQAP because procedure documents do not necessarily require the formality of change management as does an SQAP.  This suggestion is based on the assumption that the SQAP is reviewed and approved by the project Configuration Control Board (CCB) and formally placed under configuration management.

In defining what a procedure should contain it is important to understand what the objective of the procedure is.  The objective of a procedure is to provide step-by-step instructions for someone or persons performing the task.

# IDENTIFY SQA TRAINING

SQA personnel needs to identify any training that may be required to perform the SQA tasks.  Project requirements will dictate what training SQA needs to adequately perform the SQA function.

Announcements of SEPO offered courses are found in SEPO’s homepage at http://sepo.spawar.navy.mil or contact SEPO for information.

# IDENTIFY/SELECT SQA TOOLS

This paragraph in no way attempts to identify tools to assure quality of a project’s product.  But rather this paragraph describes the steps in selecting a tool to support  a software quality or SQA function or functions.

## SQA Tools Selection Process

- Define your project SQA requirements.  A prerequisite for defining SQA requirements is that project requirements must already be defined.  SQA requirements are defined in the SQAP and are based on project requirements as defined in the project’s Software Development Plan (SDP).

- Develop a Plan of Action and Milestone for selecting the SQA tool:

- Schedule a target date of when you want the vendor selected.

- Schedule the tentative dates for product demos.

- Schedule the tool evaluation period and date of selecting the best vendor.

- Schedule the date for purchasing the tool.

- Schedule the tool setup and installation.

- Schedule formal training.

- Identify the target date of when you want the tool in place.

- Establish a working group, if possible, to help identify and select the tool based on project and SQA requirements.

- Define and document SQA Tool Requirements.  Requirements would include the computer platforms that the software must reside, the operating systems of the platforms, the interface of the SQA tool with the software engineering environment, the type of software being developed, e.g., Ada, C, etc., the target computer, etc.  Considerations would include how much the project can afford on a tool, the resources to support the tool, decision to buy or develop the tool in house, doing a cost benefit analysis, etc.

- Read the Product Literature.  Know what’s out there.  A source is the Software Technology Support Center (STSC) reports on tools.  STSC reports are  available in SEPO’s Library.  Another source is surfing the World-Wide Web (WWW) for information.

- Narrow the Tools down to a workable level (3 to 5 vendors perhaps) that best meets the SQA Tool Requirements.

- Ask for a Vendor Product Demo.  Provide a copy of the SQA Tool Requirements to the Vendor.  Ask that the vendor address the tools capabilities for meeting the requirements specified in the SQA Tool Requirements document.

- Ask for an Evaluation Copy of the SQA Tool Software.  Ask for support during the evaluation period.

- Base the evaluation of the tool against the SQA Tool Requirements document.  Rate the tools using a 1 to 5 point scale with 5 being the highest.  Make a decision on the tool to buy.

# IMPROVE PROJECT SQA  PROCESSES

The SQA activity for process improvement requires:

- Understanding project and SQA processes

- Determining where inefficiencies or defects occur (root causes of defects)

- Recommending changes to project processes to improve efficiency or reduce defects

- Recommending improvements to eliminate the root causes of defects

- Recommending training courses for the project team

The purpose of this activity is for SQA to review existing project and SQA processes and report on efficiencies and areas for improvement and identify processes that need to be defined.   To improve project SQA processes, SQA needs to review and audit both project processes and SQA processes.   This will ensure that project processes and project SQA processes are consistent and compatible with one another.  Section 2 described the SQA tasks for conducting software process audits.  A method for improving project SQA processes is for SQA to conduct internal SQA reviews.  Internal SQA reviews involves compliance with the SPAWARSYSCEN SAN DIEGO CA SQA Policy, compliance with the project SQAP and SDP, and  compliance to documented SQA processes and procedures.  The method for reporting findings of a software process audit is the process audit form.  The process audit form should be used as the vehicle to initiate action for process improvement.  Process improvement may result in changes to the policy, processes, and/or procedures.

# TERMS, DEFINITIONS and ACRONYMS

## Terms and Definitions

Terms fundamental to any discussion of quality assurance include:

PROCESS.  An organized set of activities performed for a given purpose; for example, the software development process. [MIL-STD-498]

QUALITY.  The totality of features and characteristics of a product or service that bear on its ability to satisfy stated or implied needs.

QUALITY POLICY.  The overall quality intentions and direction of an organization as regards to quality, as formally expressed by top management.

QUALITY MANAGEMENT.  The aspect of overall management function that determines and implements a quality policy.

QUALITY SYSTEM.  The organization structure, responsibilities, procedures, processes and resources for implementing quality management.

SOFTWARE DEVELOPMENT PLAN (SDP).  The SDP describes a developer’s plans for conducting a software development effort.  The term “software development” is meant to include new development, modification, reuse, reengineering, maintenance, and all other activities resulting in software products.  The SDP also provides the acquirer insight into, and a tool for monitoring, the processes to be followed for software development, the methods to be used, the approach to be followed for each activity, and project schedules, organization, and resources. [MIL-STD-498]

SOFTWARE METRICS. Numerical measures of the products and processes that make up the software project.  The careful use of numerical measures can introduce precision and clarity to the process instead of opinion, informality, and open interpretation.

SOFTWARE QUALITY.  Ability of software product to satisfy specified requirements. [MIL-STD-498]

SOFTWARE QUALITY ASSURANCE.  Planned and systematic pattern of all actions necessary to provide adequate confidence that a software work product conforms to established technical requirements, and, set of activities designed to evaluate the process by which software work products are developed and maintained.

SOFTWARE QUALITY ASSURANCE PLAN (SQAP).  The SQAP describes the plans and activities of the SQA staff. [IEEE Std 730.1-1985]

SQA SPECIALIST.  Individuals who specialize in quality assurance.  An SQA specialist assists in formulating quality assurance policy and practices.  SQA’s role is to ensure that appropriate quality assurance practices are being used correctly.  SQA’s advisory role is to help project teams when plans go astray, or when special circumstances arise.

STATEMENT OF WORK (SOW).  A SOW describes tasks and directs methodologies in service acquisitions.  It may incorporate specifications that provide details covering performance.

SOFTWARE UNIT (SU).  A SU is an element in the design of a CSCI; for example, a major subdivision of a CSCI, a component of that subdivision, a class, object, module, function, routine, or database.  Software units may occur at different levels of a hierarchy and may consist of other software units.  Software units in the design may or may not have a one-to-one relationship with the code and data entities (routines, procedures, databases, data files, etc.)  that implement them or with the computer files containing those entities. [MIL-STD-498]

SOFTWARE DEVELOPMENT FILE (SDF).  A SDF as a repository for material pertinent to the development of a particular body of software.  Contents typically include (either directly or by reference) considerations, rationale, and constraints related to requirements analysis, design, and implementation; developer-internal test information; and schedule and status information. [MIL-STD-498]

## Acronyms

AI		Action Item

CCB		Configuration Control Board

CDR		Critical Design Review

CSCI		Computer Software Configuration Item

DBDD		Data Base Design Description

DCR		Document Change Request

DID		Data Item Description

DOD		Department of Defense

FCA		Functional Configuration Audit

FI		Formal Inspection

FQR		Formal Qualification Review

HWCI		Hardware Configuration Item

IDD		Interface Design Description

IRS		Interface Requirements Specification

IV&V		Independent Verification and Validation

KPA		Key Process Area

NDS		Non-Developmental Software

OCD		Operational Concept Document

PCA		Physical Configuration Audit

PDR		Preliminary Design Review

PRR		Product Readiness Review

SDD		Software Design Document

SDF		Software Development File

SDP		Software Development Plan

SDR		System Design Review

SEI		Software Engineering Institute

SEPO		Software Engineering Process Office

SOW		Statement of Work

SQA		Software Quality Assurance

SQAP		Software Quality Assurance Plan

SRR		System Requirements Review

SRS		Software Requirements Specification

SSDD		System/Subsystem Design Description

SSR		Software Specification Review

SSS		System/Subsystem Specification

STSC		Software Technology Support Center

SW-CMM	Software Capability Maturity Model

TRR		Test Readiness Review

UDF		Unit Development Folder

WBS		Work Breakdown Structure

WWW		World-Wide Web

DOCUMENT CHANGE REQUEST (DCR)

| Document Title: ñññññ | Tracking Number: ñññññ |
| --- | --- |
| Name of Submitting Organization: ñññññ |  |
| Organization Contact: ñññññ | Phone: ñññññ |
| Mailing Address: ñññññ |  |
| Short Title: ñññññ | Date: ñññññ |
| Change Location: ñññññ (use section #, figure #, table #, etc.) |  |
| Proposed change: ñññññ |  |
| Rational for Change: ñññññ |  |
| Note: For the Software Engineering Process Office (SEPO) to take appropriate action on a change request, please provide a clear description of the recommended change along with supporting rationale. Send to: Commanding Officer, Space and Naval Warfare Systems Center, D13, 53560 Hull Street, San Diego, CA 92152-5001 or Fax to: (619)553-6249 or Email to: sepo.spawar.navy.mil DCR Form 9/1997 |  |