Impact Analysis Checklist for Requirements Changes

##### Implications of the Proposed Change

- Identify any existing requirements in the baseline that conflict with the proposed change.

- Identify any other pending requirement changes that conflict with the proposed change.

- What are the consequences of not making the change?

- What are possible adverse side effects or other risks of making the proposed change?

- Will the proposed change adversely affect performance requirements or other quality attributes?

- Is the proposed change feasible within known technical constraints and current staff skills?

- Will the proposed change place unacceptable demands on any computer resources required for the development, test, or host environments?

- Must any tools be acquired to implement and test the change?

- How will the proposed change affect the sequence, dependencies, effort, or scheduled duration of any tasks currently in the project plan?

- Will prototyping or other user input be required to verify the proposed change?

- How much effort that has already been invested in the project will be lost if this change is accepted?

- Will the proposed change cause an increase in product unit cost, such as by increasing third-party product licensing fees?

- Will the change affect any marketing, manufacturing, training, or customer support plans?

##### Software Elements Affected by the Proposed Change

- Identify any user interface changes, additions, or deletions required.

- Identify any changes, additions, or deletions required in reports, databases, or data files.

- Identify the design components that must be created, modified, or deleted.

- Identify the source code files that must be created, modified, or deleted.

- Identify any changes required in build files.

- Identify existing unit, integration, and system test cases that must be modified or deleted.

- Estimate the number of new unit, integration, and system test cases that will be required.

- Identify any help screens, user manuals, training materials, or other documentation that must be created or modified.

- Identify any other systems, applications, libraries, or hardware components affected by the change.

- Identify any third party software that must be purchased.

- Identify any impact the proposed change will have on the project’s software project management plan, software quality assurance plan, software configuration management plan, or other plans.

- Identify work products that must be reviewed after they are modified.

Effort Estimation for a Requirements Change

| Effort (Labor Hours) | Task |
| --- | --- |
|  | Update the SRS or requirements database with the new requirement |
|  | Develop and evaluate prototype |
|  | Create new design components |
|  | Modify existing design components |
|  | Develop new user interface components |
|  | Modify existing user interface components |
|  | Develop new user publications and help screens |
|  | Modify existing user publications and help screens |
|  | Develop new source code |
|  | Modify existing source code |
|  | Purchase and integrate third party software |
|  | Modify build files |
|  | Develop new unit and integration tests |
|  | Modify existing unit and integration tests |
|  | Perform unit and integration testing after implementation |
|  | Write new system test cases |
|  | Modify existing system test cases |
|  | Modify automated test drivers |
|  | Perform regression testing at unit, integration, and system levels |
|  | Develop new reports |
|  | Modify existing reports |
|  | Develop new database elements |
|  | Modify existing database elements |
|  | Develop new data files |
|  | Modify existing data files |
|  | Modify various project plans |
|  | Update other documentation |
|  | Update requirements traceability matrix |
|  | Review work products |
|  | Perform rework following reviews and testing |
|  | TOTAL ESTIMATED EFFORT |

Procedure:

- Identify the subset of the above tasks that will have to be done.

- Allocate resources to tasks.

- Estimate effort required for pertinent tasks listed above, based on assigned resources.

- Total the effort estimates.

- Sequence tasks and identify predecessors.

- Determine whether change is on the project’s critical path.

- Estimate schedule and cost impact.

Impact Analysis Report Template

Change Request ID:	______________

Title:	______________________________________________________

Description:	______________________________________________________

______________________________________________________

Analyst: 	__________________________

Date Prepared: 	__________________________

Prioritization Estimates:

Relative Benefit:		 (1-9)

Relative Penalty:		 (1-9)

Relative Cost:		 (1-9)

Relative Risk:		 (1-9)

Calculated Priority:

Estimated total effort:	___________ labor hours

Estimated lost effort:	___________ labor hours

Estimated schedule impact:	___________ days

Additional cost impact:	___________ dollars

Quality impact:	_______________________________________________		_______________________________________________

Other requirements affected:	____________________________________________________

____________________________________________________

Other tasks affected:	____________________________________________________

____________________________________________________

Plans to be updated:	____________________________________________________

Integration issues:	____________________________________________________

Life cycle cost issues:	____________________________________________________

Other components to examine	____________________________________________________

for possible changes:		____________________________________________________